## Job Tracker
PSS JOB TRACKER — Printed Shadenet Solutions
JOB # | CLIENT | CONTACT | LIN. METRES | HEIGHT | COLOURS | CLOTH SUPPLY | QUOTE (R) | DEPOSIT (R) | DEPOSIT PAID | BALANCE (R) | BALANCE PAID | STATUS | DEADLINE | DISPATCH DATE | ARTWORK OK | NOTES
Grow | David | 664724174 | 200 | 1.8 | red on black net | PSS Supplied | 43645.38 | 21822.69 | yes | 21822.69 |  | IN PRODUCTION | 2026-03-27 |  | YES
Sunbet | Thato | 26776056091 | 33 panels |  | blue | Client Supplied | 21131 | 10565.5 |  | 10565.5 | yes | ON DECK | 2026-04-03 |  | YES
EMG | Nico |  | 70 | 1.8 | blue | Client Supplied
Rovis

## Status Guide
JOB STATUS REFERENCE
STATUS | MEANING | ACTION REQUIRED
ENQUIRY | Initial contact received — not yet quoted | Qualify client. Send quote within same day.
QUOTED | Quote sent — awaiting client confirmation | Follow up after 5 days if no response.
DEPOSIT DUE | Job confirmed — deposit invoice sent, not yet paid | Chase if unpaid after 5 days. No production until paid.
IN PRODUCTION | Deposit received — job on the print floor | Daani has job sheet. Monitor deadline.
DISPATCHED | Job couriered — balance invoice sent | Confirm delivery. Chase balance at 7 days if unpaid.
COMPLETE | Balance received — job closed | Take photo for portfolio. Update tracker.
ON HOLD | Job paused — client delay or awaiting artwork | Note reason. Follow up weekly.
CANCELLED | Job cancelled | Note reason. Do not delete row.

## Weekly Review
MONDAY WEEKLY JOB REVIEW
Week of:
REVIEW CHECKLIST
CHECK | JOB #(s) | CLIENT | DAYS OUTSTANDING | ACTION
STUCK AT DEPOSIT DUE (5+ days unpaid)
QUOTED — no response after 7 days
DEADLINES in next 14 days
JOBS IN PRODUCTION — on track?
ARTWORK outstanding
OVERDUE BALANCES
NOTES / ACTIONS THIS WEEK